## UserStoryBurndown chart
To complete and integrate all user stories that have been started. Assumption: 1 day = 6 hours | Working Days per Sprint | Planned sub-tasks
Sprint Backlog | 15 | 11 | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday | Friday
Working Days |  |  | 11 | 10.1689 | 9.3867 | 8.6044 | 7.8222 | 7.04 | 6.2578 | 5.4756 | 4.6933 | 3.9111 | 3.1289 | 2.3467 | 1.5644 | 0.78222 | 3.0947e-15
Task Description | Team | Sub-tasks Remaining | 11 | 11 | 9 | 8 | 8 | 7 | 7 | 6 | 5 | 4 | 4 | 3 | 1 | 1 | 0
| Project X | Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## User Story List
ID | Priority | Description | Story Points | Sprint | Comments
1 | 1 | Research required technologies | 48 | 0
2 | 2 | Install & Sync technologies | 48 | 0
3 | 3 | Design Database | 16 | 0
4 | 4 | Setup Database | 4 | 0
5 | 5 | Create HTML to upload excel sheets | 8 | 0 | USER STORY 1
6 | 6 | Code interaction between HTML & database | 16 | 0 | Sub-Task
7 | 7 | Create rules for validating data | 4 | 0 | Sub-Task
8 | 8 | Code to check cells for valid data | 16 | 0 | USER STORY 3
9 | 9 | Code action for non-compliant data | 16 | 0 | Sub-Task
10 | 10 | Create HTML for IMSI input | 4 | 0 | USER STORY 4
11 | 11 | Code to interact between HTML & database | 8 | 0 | Sub-Task